## Milestones
Budget |  |  | Milestone Timelines |  |  |  | Tranche Disbursement Schedule
[7 empty] | Timeline | Amount to be released (INR) inclusive of GST | Milestone/Deliverables that will be completed by the timeline
Sr. No. | Item | Total (Rs.) | S No | Milestone/Deliverable | Time Period | Remarks
1 | Manpower | 0 | 1 | Project Beginning (T0) | T0 | Project plan, stakeholder alignment, BOM freeze | Project Start Date (T0) | 8235 | M1 monitor build and dashboard
2 | Equipment | 15600 | 2 | Milestone 1: Requirements and monitor prototype | T0 + 2 months | M1 calibrated; TankScore validated; dashboard served from the tank unit | T0 + 06 months | 9415 | H1 home unit and C1 cleaning arm
3 | Consumables | 0 | 3 | Milestone 2: Home unit and dashboard | T0 + 4 months | H1 TFT + pump control installed; dashboard and session log complete | T0 + 12 months | 5937 | Field validation and evidence pack
4 | Travel | 0 | 4 | Milestone 3: Cleaning arm | T0 + 8 months | C1 built; three-ring cycle executed; coverage and repeatability measured | Total | 23587
5 | Miscellaneous expenses | 0 | 5 | Milestone 4: Field validation | T0 + 12 months | Three installations, 90 days of data, TRL 6+ evidence pack
6 | Contingency (max @5% of 10) | 780 |  | Total |  |  | Total
7 | Sub total | 16380
8 | Overhead | 3276
9 | Faculty Fee (inclusive of all overheads/ institute share etc) @maximum of 20%of total project value | 3931
10 | Total (7+8 +9) | 23587
11 | GST (@18% of 10) | 0
12 | Grant Total (10+11) | 23587

## Budget
Grant Total (INR) - Full proposal build: 23,587
Milestone Expenditure Sheet |  |  | Tranche 1 Amount in Rs. XXXXXX | Tranche 2 Amount in Rs. XXXXXX | Tranche 3 Amount in Rs. XXXXXX | Add columns
Sr.No. | Expenditure Heads | Total Funding Amount | Budgeted Amount | Budgeted Amount | Budgeted Amount
1 | Manpower
2 | Equipment
3 | Consumables
4 | Travel
5 | Miscellaneous expenses
6 | Manpower | 0
7 | Equipment (Exclusive of GST) | 15600
8 | Contingency (max 5%) | 780
9 | Sub total | 16380
10 | Overhead (max 20%) | 3276
11 | Faculty Fee (max 20%) | 3931
12 | Total (7+8+9) | 23587
80% of the tranche fund should be utilized before claiming for the next tranche.